## Features
ID | Title | Description | Plaform | Status | Statuses
1 | Prototype UI | Program the initial design of the app from Frigma to Flutter app | Flutter | Completed | Completed | 17
4 | Fetch Data | The app should be able to retrieve and display the data from backend | Flutter | Completed | In Progress | 6
6 | Send Data | The app should be able to send data to backend | Flutter | Completed | To Do | 6
7 | Number Padlock Game | Make a guessing game with but using number padlock to input numbers | Flutter | Completed | Total | 29
8 | Color Game | A game where the user will choose a color and a color cube that will randomly select a winning color | Flutter | Completed
11 | Slot Machine Game | Make a slot machine game that need to get "IMUS" combination to win | Flutter | Completed | Platfrorm
12 | Shuffle Cup Game | Make a shuffle cup game | Flutter | Completed | Flutter | 21
13 | Memory Card Game | Make a memory game using classic cards as items | Flutter | Completed | Laravel | 8
9 | Change the App Name | Change the app name to be related or connect to the Mayor | Flutter | Completed | Total | 29
19 | Decrease the number of Cards | Decrease the number of pair of cards in memory card game | Flutter | Completed
17 | Improve Displaying Data | Improve the efficiency of displaying data from backend | Flutter | Completed | PROGRESS | 58.62%
29 | Memory Cards Focusable | Make the memory cards have an indication of being focused | Flutter | Completed
5 | Display Images and Video Efficiently | The app should be able to fetch and display images and video efficiently | Flutter | In Progress
21 | Proper Project Structure | Use a proper or standard project structure for the project | Flutter | In Progress
14 | Compatible Remote Controls | Make sure that android tv box remote can control the application effectively. The user should be able to interact with the application easily | Flutter | In Progress
18 | Focus State Enhancement | Enhance the focus state display of buttons and other widgets to make it noticeable for users | Flutter | In Progress
20 | Improve Color Game | Make the color selection to two and color selector to three. Make the color selector animate as cube rolling. | Flutter | In Progress
23 | Improve Number Padlock Game | Improve the design, animation, and mechanics of number padlock game | Flutter | In Progress
15 | Improve UI | Improve the UI to make it appealing to the users | Flutter | To Do
22 | Improve Slot Machine Game | Improve the design and animation of slot machine game | Flutter | To Do
27 | Unit Testing (AA TV) | Implement unit testing for AA TV | Flutter | To Do
2 | Protoype Backend | Create a function where the backend could receive the data from the app | Laravel | Completed
3 | API Implementation | Backend should be able to store data where the app could retrieve it | Laravel | Completed
10 | Video and Image Upload | Can be able to upload, preview, view, edit, and delete videos and images. | Laravel | Completed
24 | Back-end Login System | Implement login system for te backend site of the app | Laravel | Completed
16 | Improve API Communication | Improve the efficiency of communication between the app and the backend | Laravel | Completed
25 | Back-end UI | Implement a proper UI for the backend site | Laravel | To Do
26 | Back-end DataTables | Use a proper datatables for displaying data in back-end | Laravel | To Do
28 | Unit Testing (Back-end) | Implement unit testing for AA TV Back-end | Laravel | To Do
29
30
31
32
33
34
35
36
37
38
39
40

## BUGS
ID | Title | Description | Plaform | Status | Statuses
BUG-000001 | Remote Control Error | Pressing the ‘OK’ button of the remote of android tv box ‘Pendoo X12’ causes an error in debug mode | Flutter | To Do | Solved | 1
BUG-000002 | Video Preview Error | Video can’t play when displaying it in view/edit modal | Laravel | Solved | Still Fixing | 0
BUG-000003 |  |  |  |  | To Do | 1
BUG-000004 |  |  |  |  | Total | 2
BUG-000005
BUG-000006 |  |  |  |  | Platfrorm
BUG-000007 |  |  |  |  | Flutter | 1
BUG-000008 |  |  |  |  | Laravel | 1
BUG-000009 |  |  |  |  | Total | 2
BUG-000010
BUG-000011
BUG-000012
BUG-000013
BUG-000014
BUG-000015